## Weekly Progress
B.M.S. COLLEGE OF ENGINEERING
Project Work 2 ¦ Course code: 24AM7PWPW2
Project title | PolicyGPT: An AI-Driven Policy Intelligence and Assistance Platform for Government Schemes
Team members | Sahana B.K. (1BM23AI162); Shamratha G. (1BM23AI173); Suniksha Priya (1BM23AI192)
Guide | Sanket S. Kulkarni, Assistant Professor, Department of Machine Learning
Week | Date | Task completed this week | Task planned for next week | Issues and challenges | Remarks by guide | Students’ signature | Guide’s signature
1 | 27 Jun–3 Jul 2026 | Converted Project Work 1 design into implementation backlog and finalized API/corpus architecture. | Create repository, environment and seed corpus. | Need verified policy sources and provider-independent fallback. |  | [sign] | [sign]
2 | 4–10 Jul 2026 | Created FastAPI service, SQLite schema, static UI and Docker files. | Implement corpus ingestion and retrieval. | Keeping deployment simple for a prototype. |  | [sign] | [sign]
3 | 11–17 Jul 2026 | Implemented domain routing and hybrid lexical-semantic retrieval. | Add generation, citations and eligibility checks. | Semantic model dependency avoided with deterministic baseline. |  | [sign] | [sign]
4 | 18–24 Jul 2026 | Added generation, profile-aware eligibility and claim-level validation. | Add report export and session history. | Missing profile fields remain unknown rather than rejected. |  | [sign] | [sign]
5 | 25–31 Jul 2026 | Added bounded confidence/risk repair pass and Markdown reports. | Add tests and improve UI. | Avoiding unbounded retries and unsupported claims. |  | [sign] | [sign]
6 | 1–7 Aug 2026 | Integrated tests, source links, warning messages and SQLite history. | Run end-to-end demo and fix defects. | Validate citation coverage on ambiguous queries. |  | [sign] | [sign]
7 | 8–14 Aug 2026 | Completed API/UI smoke testing and Docker configuration. | Prepare Review 1 slides and rubric evidence. | Documenting limitations and official-source responsibility. |  | [sign] | [sign]
8 | 17–24 Aug 2026 | Prepared presentation content, demo script and next-phase enhancement list. | Incorporate panel feedback and expand verified corpus. | Need guide approval for corpus scope and deployment target. |  | [sign] | [sign]
Guide and Panel Member Signatures |  |  |  |  | HOD Signature